## Slide 1
Re
SWAT PROGRAM
TTI Presentation
Revised on 04/11/2017

## Slide 2
    On 01-11-17 Mayor Turner rolled out a new initiative to proactively reduce drainage problems that are not directly attributed to overflow from the bayous.

## Slide 3: SWAT - Storm Water Action Team
Improvements
Ditch Widening
Driveway Culvert Replacement
Inlet Replacement
Side Lot Swales
Sewer Line Replacements/Repairs (collapsed outfalls)
Detention Ponds
Funding
$10 million approved by City Council on January 11, 2017
Start with 22 projects/2 in each council district
Issues
Department Resources
Policy Changes
  De minimus Storage
  Roadside Ditch Driveways
  Roadside Ditch/Off-Road Ditch Obstructions
Ditch Widening
  Roadside Ditch Driveways
  Roadside Ditch/Off-Road Ditch Obstructions

## Slide 4: SWAT – Team Composition
Composition Duties
PWE Engineering Meet residents
PWE Maintenance Field visit flooding site
Engineering Consultant (if necessary) Evaluate flooding cause
Contractors Formulate potential solutions
Design solutions (In- house/Consultants)
Support Construct improvements (In-
Legal house/Contractors)
DON
Community Leadership
Notes: Project locations will be determined by reviewing 311 calls, non-riverine structural flooding locations, and known areas with drainage concerns. Projects will be developed by investigating and inspecting the system and developing an assessment/work plan for addressing the area(s) of highest need.

## Slide 5: SWAT Project Map
Revised
Notes: Initial SWAT Project Rollout

## Slide 6
UPDATE

## Slide 7: SWAT – Status of Projects
Initial Roll Out: 22 Projects
Forecast: ~25 Additional Projects
Backlog: 100’s Projects
Status (as of 04/11/17)
  Completed: 3
  In Construction: 6
  In Design: 5
  NTP Pending: 6
  Reconfigured DR 2015: 2
Notes: Status of Initial Roll Out projects as of 4/10/2017

## Slide 8: SWAT Project Map (As of 4/11/2017)
Notes: Map showing status of projects by district as of 4/10/2017

## Slide 9: District A – Project 1
10058 Briarwild Ln.
(N - Warwana Rd.; S - Briarwild Ln.;
E - Gessner Rd.; W - Witte Rd.)
Drainage Issues:
Culverts undersized, collapsed or
not set to proper flow line
Silted ditch flow lines and culverts
In Design

## Slide 10: District A – Project 2
2113 Woodvine Dr.
(from Long Point Rd.
to Turquoise Ln.)
Drainage Issues:
Needs Clear and Grubbing/
Re-establishment
Ditch ID: W138-00-00-A & B
Construction
NTP Pending

## Slide 11
District B – Project 1
Greater Fifth Ward (N- Farmer St.; S- Chisum St.; E - Wipprecht St. & W - Yates St.)
Drainage Issues: Culverts undersized, collapsed or not set to proper flow line
Silted ditch flow lines and culverts
In Design

## Slide 12: District B – Project 2
Trinity/Houston Gardens (N - Weaver Rd.; S - Crosstimbers St.; E - Lavender St.; W - Painter St.)
Drainage Issues: Culverts undersized, collapsed or not set to proper flow line
Silted ditch flow lines and culverts
In Design

## Slide 13: District C – Project 1
5942 Greenmont Dr.
Drainage Issues: 36-inch outfall has collapsed and caused cave-in

## Slide 14: District C – Project 2
3600 Flora St.
Drainage Issues: Existing culvert/grate failure blocking proper drainage
BEFORE
AFTER

## Slide 15: District C – Project 2
3600 Flora St.
Drainage Issues: Existing culvert/grate failure blocking proper drainage
Subject: SWAT Project Westmoreland
“Dear Council Member Cohen,
The Officers and Board of the Westmoreland Civic Association would like to express our sincere appreciation for the recent completion of a SWAT project in our neighborhood. The project was completed in a timely manor and with minimum disruption of traffic flow. Thank you for representing District C.”
David Krentz
President, Westmoreland Civic Association
Notes: Thank you letter received from President of Westmoreland Civic Association.

## Slide 16: District D – Project 1
7300 Calais Rd. (from Calais Rd. to St. Lo Rd.)
Drainage Issues: Needs Clear and Grubbing/ Re-establishment
Ditch ID: DUNK-00-05-A, B
Construction
NTP Pending

## Slide 17: District D – Project 2
4007 Botany Ln.
Drainage Issues: Needs Clear and Grubbing/ Re-establishment
Ditch ID: C127-01-00-A
Construction
NTP Pending

## Slide 18: District E – Project 1
2440 Albright Dr. (from Leprechaun St. to Martinville Dr.)
Drainage Issues: Needs Clear and Grubbing/ Re-establishment
Ditch ID: C106-05-00-A
BEFORE
AFTER

## Slide 19: District E – Project 1
2440 Albright Dr. (from Leprechaun St. to Martinville Dr.)
Drainage Issues: Needs Clear and Grubbing/ Re-establishment
Ditch ID: C106-05-00-A
BEFORE
AFTER
Subject: Drainage project
“Mr. Bryant,
I want to again thank you and your crew for the excellent work you did in clearing our storm drainage pipes. I feel secure in the knowledge that my street, Leprechaun Street, Houston, TX 77017 will drain without obstruction in the future. Getting rid of the 18-inches of sludge in the concrete pipe feeding into the new retention pond will give relief not only to my street but also to the 170+ homes in the adjacent subdivision, and will allow our storm water to freely flow away down the recently cleaned Ditch #C106-05. Your guys did a thorough and efficient job, and were courteous and personable to my wife and I, and we appreciate meeting you as the work continued. It is good to know that management takes an active interest in our area.
Have a wonderful week.”
Baxter Williams
Notes: Thank you letter received from resident.

## Slide 20: District E – Project 2
531 Keith Ave. (From S. Shaver St. to Mize Rd.)
Drainage Issues:
Needs Clear and Grubbing/ Re-establishment
Ditch ID: C106-08-04-A
BEFORE
Construction

## Slide 21: District F – Project 1
Tanglewilde - Westmont Area (from Jeanetta St. to Westerland Dr.)
Drainage Issues: Needs Clear and Grubbing/ Re-establishment
Ditch ID: W147-00-00-A
Notes: Work Authorization issued for 4/10/17 Contractor has not given actual start date.

## Slide 22: District F – Project 2
Bellaire West Detention Pond
Drainage Issues: Needs Clear and Grubbing/ Re-establishment
Notes: WA issued for 4/10/17. Contractor has not given actual start date.

## Slide 23: District G – Project 1
614 Woodbend Ln.
Drainage Issues: 120-inch storm sewer line has eroded at bottom
and caused multiple small cave-ins
Notes: Working on Change Order for Spin Casting 120” pipe.

## Slide 24: District G – Project 2
1209 S Dairy Ashford Rd.
Drainage Issues: 36-inch outfall has collapsed at Terry Hershey Park and caused a cave-in
BEFORE
Construction
Notes: Waiting on spin cast of final section of 36” pipe.

## Slide 25: District H – Project 1
Northside/ Northline Area Roadside Ditch Project 1
(N - Turner Dr.; S - Luther St.;
E - Clark Rd.; W - Fulton St.)
Drainage Issues:
Culverts undersized, collapsed or not set to proper flow line
Silted ditch flow lines and culverts
Reconfigured
DR 2015

## Slide 26: District H – Project 2
Northside/ Northline Area Roadside Ditch Project 2
(N - Wellington St.; S - Keel Rd.; E - O'Donnell Dr.;
W - Fulton St.)
Drainage Issues:
Culverts undersized, collapsed or not set to proper flow line
Silted ditch flow lines and culverts
Reconfigured
DR 2015

## Slide 27: District I – Project 1
Plum Creek Clean Up (Part A) (from I-610 E. to Coral St.)
Drainage Issues: Needs Clear and Grubbing/ Re-establishment
Ditch ID: C102-00-00-M
Construction
NTP Pending

## Slide 28: District I – Project 2
Plum Creek Clean Up (Part B)
(Coral St. to Office City Dr.)
Drainage Issues:
Needs Clear and Grubbing/ Re-establishment
Ditch ID: C102-00-00-L
Construction
NTP Pending

## Slide 29: District J – Project 1
9238 Tooley Dr.
Drainage Issues: 60-inch outfall has collapsed and caused a cave-in
Construction
NTP Pending

## Slide 30: District J – Project 2
Bedford Project
(N - Beltway 8; S - Dorrance Rd.; E - Bedford Dr.; W - Dover St.)
Drainage Issues:
Culverts undersized, collapsed or not set to proper flow line
Silted ditch flow lines and culverts
In Design

## Slide 31: District K – Project 1
11507 Bowlan Ln. (Westbury Pkg. 2)
Drainage Issues:
24-inch outfall collapse

## Slide 32: District K – Project 1
BEFORE
In Construction
AFTER
11507 Bowlan Ln. (Westbury Pkg. 2)
Drainage Issues:
24-inch outfall collapse

## Slide 33: District K – Project 2
Cambridge Village Park (N - Allum St.; S - Lotus St.; E - Nitida St.; W - S. Post Oak Rd.)
Drainage Issues: Culverts undersized, collapsed or not set to proper flow line
Silted ditch flow lines and culverts
In Design

## Slide 34: All Projects Identified (as of 4/11/17)
Projects by Council District and Asset Count
Projects by Asset Type

## Slide 35: SWAT Projects Cost Estimate (as of 4/11/17)

## Slide 36
Ideas for potential SWAT projects in your district?
Contact:
Stephen Costello, 832-393-0811, stephen.costello@houstontx.gov
Sallie Alcorn, 832-393-1123, sallie.alcorn@houstontx.gov